## Sheet1
Ticket ID | Ticket Description | Defect Priority | Complexity | Steps to reproduce | Ticket Status | Reported By | Reporting Date | Assigned To | Assignment Status | Target Date | Resolution | Remarks
1 | In grid view update join date is not updating in edit functionality | Priority 2 | Medium | 1. Login with Admin credentials. 2. Click on "Working Employees" under "Employee Support" main tab. 3. List of all user in the system are displayed. 4. Click on "Edit" available for any of the record displayed. 5. Modify the "Join Date" field and click on "Update". 6. The record is not updating to the modified value. | UnAssigned |  |  | Sohan | Yet to Start
2 | When 1 item is present in dropdown by default the values related to it is not displaying in grid. It is getting displayed only in selection changed event for morethan 1 item. | Priority 2 | Medium | 1. Login with Admin credentials. 2. Click on "Employee on Policy" under main tab "Search". 3. When Page gets loaded the data for the first item/designation in the dropdown is not getting displayed. 4. Change the dropdown value, the data is getting bind for this value. | UnAssigned |  |  | Vinod | Yet to Start
3 | when 1 item is present in dropdown by default the values related to it is not displaying in grid. It is getting displayed only in selection changed event for morethan 1 item. | Priority 2 | Medium | 1. Login with Admin credentials. 2. Click on "Policy on Employee" under main tab "Search". 3. When Page gets loaded the data for the first item/policy in the dropdown is not getting displayed. 4. Change the dropdown value, the data is getting bind for this value. | UnAssigned |  |  | Puja | Yet to Start
4 | Delete request button funtionality missing | Priority 1 | Complex | 1. Login with Admin credentials 2. Click on "Request Status" tab. It displays list of request by the user. 3. Click on "Check For Status" link for any of the record. It displays the details of the request. 4. Click on "Delete Request". Request is not getting deleted. Functionality is missing. | UnAssigned |  |  | Sud | Yet to Start
5 | when first company is added the id in DB is taken as zero. It should start form 1 | Priority 1 | Medium | 1. Login with Admin credentials. 2. Click on "Add Insurance" under "Add Resouce" main tab. 3. Provide all data of the company and click on save. 4. The data is getting saved in DB but with Company ID as "0" zero for the first record. 5. Click on "Add Policy on Employee" under "Employee support" main tab. 6. Click on "Company Id" drop down it is displaying 0 as one of the id. | UnAssigned |  |  | Sud | Yet to Start
6 | Delete user and search for Employee on policy, the policy tagged to deleted employee is displayed. The deleted user info shouldnot be displayed. | Priority 1 | Complex | 1. Login with Admin credentials. 2. Click on "Working Employees" under "Employee Support" main tab. 3. List of all user in the system are displayed. 4. Click on "Delete" available for any of the user who has already policy mapped. 5. The user record gets deleted. 6. Click on "Employee on Policy" under "Search" main tab. 7. Search for this deleted user. The user data is getting displayed. 8. As the user is deleted user related info should also be deleted. | UnAssigned |  |  | Sohan | Yet to Start
7 | Cancel is not clearing join date field | Priority 3 | Simple | 1. Login with Admin credentials 2. Click on "Add employee" under "Employee Support" main tab. 3. Provide data in all fields. 4. Click on "Cancel" button. 5. The data is getting reset except for "Join Date" field. | UnAssigned |  |  | Sourodeep | Yet to Start
8 | When policy id is slected policy name, policy amount and policy EMI are updated by default but which are editable. Make these fileds non editable. when Company id is slected company name is updated by default but which is editable. Make this filed non editable. | Priority 3 | Simple | 1. Login with Admin credentials. 2. Click on "Add policy to Employee" under "Employee Support". 3. Select any of the policy id from dropdown. 4. Automatically Policy Name, Policy EMI and Policy Amount are getting updated for that Policy Id and these fields are editable. 5. Make these fields non editable as they are dependent on policy id. | UnAssigned |  |  | Sourodeep | Yet to Start
9 | Phone number validation missing (accepting alphabets) | Priority 3 | Simple | 1. Login with Admin credentials. 2. Click on "Working Employees" under "Employee Support" main tab. 3. List of all user in the system are displayed. 4. Click on "Edit" available for any of the record displayed. 5. Modify the "Phone number" field to alphabets and click on "Update". 6. The record is not updating to the modified value. 7. Provide a validation so that only numeric is accepted for phone number field. | UnAssigned |  |  | Souradeep | Yet to Start
10 | When no claims are added to employee the page is throwing error - no rows at position zero | Priority 1 | Complex | 1. Login with Employee credentials. 2. Click on "search claims" under "Search" tab. 3. It is throwing error when the user is not having any policies added to his/her account. 4. The message "No claims available" should be displayed. | UnAssigned |  |  | Puja | Yet to Start
11 | Navigate from Request status screen click on check request status it redirects to form status. For the old employee who does not have policy the "Add policy to employee" button will be enabled. Click on this button this will redirect to add policy on employee page where the data is not filled by default only employee id is updated. | Priority 2 | Complex | 1. Login with Admin credentials 2. Click on "Request Status" tab. It displays list of request by the user. 3. Click on "Check For Status" link for any of the record. It displays the details of the request. 4. Click on "Add Policy to Employee". This button will be enabled when user joining date is before 6 months and user does not have any policy mapped. 5. User is redirected to "Add Policy to Employee" screen but all the fields are blank. 6. Fill the fields with the data user is requested for. | UnAssigned |  |  | Puja | Yet to Start
12 | In the designation dropdownlist values are duplicated. Remove duplicate values. | Priority 2 | Complex | 1. Login with Admin credentials. 2. Click on "Employee on Policy" under main tab "Search". 3. A dropdown with all designations available in the system is displayed. 4. The values are duplicated i.e, if system is having 2 user with designation as "Associate" then it is displayed 2 times in the dropdown. 5. Designation should not be duplicated. | UnAssigned |  |  | Sud | Yet to Start
13 | In the policy dropdownlist values are duplicated. Remove duplicate values. | Priority 2 | Complex | 1. Login with Admin credentials. 2. Click on "Policy on Employee" under main tab "Search". 3. A dropdown with all Policies available in the system is displayed. 4. The values are duplicated i.e, if system is having 2 user with policy as "Vehicle" then it is displayed 2 times in the dropdown. 5. Policy names should not be duplicated. | UnAssigned |  |  | Sohan | Yet to Start
14 | Change the order of records displayed. Recent request should display first. Also display 6 records per page instead of 4. | Priority 3 | Simple | 1. Login with Admin credentials 2. Click on "Request Status" tab. It displays list of request by the user. 3. Change the order of the records basrd on request date. Recent request should be on top. 4. Modify the no of items displayed per page fron 4 to 6. | UnAssigned |  |  | Souradeep | Yet to Start
15 | No action taking place on click of submit in feedback screen. Save data to db and display successful message once saved. Also add regular expression to email field. | Priority 1 | Complex | 1. Browse the application as Non member 2. Click on "Feedback" link" 3. Provide data in all fields and click on "Save". 4. No action taking place. The data should be saved into database and appropriate message should be displayed to the user. | UnAssigned |  |  | Vinod | Yet to Start
16 | Contact us page is not working. Submit click event is not saving data. Please add a table in db to save data. Also add required field validations to all controls. Add regular expression validators to email and phone number. Once data is saved display successful message. | Priority 1 | Complex | 1. Browse the application as Non member 2. Click on "Contact Us" link" 3. Provide data in all fields and click on "Save". 4. No action taking place. The data should be saved into database and appropriate message should be displayed to the user. | UnAssigned |  |  | Vinod | Yet to Start
Yet to Start
Yet to Start
Yet to Start
Yet to Start
Yet to Start
Yet to Start
Yet to Start
Yet to Start
Yet to Start
Yet to Start
Yet to Start
Yet to Start
Yet to Start
Yet to Start
Yet to Start
Yet to Start
Yet to Start
Yet to Start
Yet to Start
Yet to Start
Yet to Start
Yet to Start
Yet to Start
Yet to Start
Yet to Start
Yet to Start
Yet to Start
Yet to Start
Yet to Start
Yet to Start
Yet to Start
Yet to Start
Yet to Start
Yet to Start
Yet to Start
Yet to Start
Yet to Start
Yet to Start
Yet to Start
Yet to Start
Yet to Start
Yet to Start
Yet to Start
Yet to Start
Yet to Start
Yet to Start
Yet to Start
Yet to Start
Yet to Start
Yet to Start
Yet to Start
Yet to Start
Yet to Start
Yet to Start
Yet to Start
Yet to Start
Yet to Start
Yet to Start
Yet to Start
Yet to Start
Yet to Start
Yet to Start
Yet to Start
Yet to Start
Yet to Start
Yet to Start
Yet to Start
Yet to Start
Yet to Start
Yet to Start
Yet to Start
Yet to Start
Yet to Start
Yet to Start
Yet to Start
Yet to Start
Yet to Start
Yet to Start
Yet to Start
Yet to Start
Yet to Start
Yet to Start
Yet to Start
Yet to Start
Yet to Start
Yet to Start
Yet to Start
Yet to Start
Yet to Start
Yet to Start
Yet to Start
Yet to Start
Yet to Start
Yet to Start
Yet to Start
Yet to Start
Yet to Start
Yet to Start
Yet to Start
Yet to Start
Yet to Start
Yet to Start
Yet to Start
Yet to Start
Yet to Start
Yet to Start
Yet to Start
Yet to Start
Yet to Start
Yet to Start
Yet to Start
Yet to Start
Yet to Start
Yet to Start
Yet to Start
Yet to Start
Yet to Start
Yet to Start
Yet to Start
Yet to Start
Yet to Start
Yet to Start
Yet to Start
Yet to Start
Yet to Start
Yet to Start
Yet to Start
Yet to Start
Yet to Start
Yet to Start
Yet to Start
Yet to Start
Yet to Start
Yet to Start
Yet to Start
Yet to Start
Yet to Start
Yet to Start
Yet to Start
Yet to Start
Yet to Start
Yet to Start
Yet to Start
Yet to Start
Yet to Start
Yet to Start
Yet to Start
Yet to Start
Yet to Start
Yet to Start
Yet to Start
Yet to Start
Yet to Start
Yet to Start
Yet to Start
Yet to Start
Yet to Start
Yet to Start
Yet to Start
Yet to Start
Yet to Start
Yet to Start
Yet to Start
Yet to Start
Yet to Start
Yet to Start
Yet to Start
Yet to Start
Yet to Start
Yet to Start
Yet to Start
Yet to Start
Yet to Start
Yet to Start
Yet to Start
Yet to Start
Yet to Start
Yet to Start
Yet to Start
Yet to Start
Yet to Start
Yet to Start
Yet to Start
Yet to Start
Yet to Start
Yet to Start
Yet to Start
Yet to Start
Yet to Start
Yet to Start
Yet to Start
Yet to Start
Yet to Start
Yet to Start
Yet to Start
Yet to Start
Yet to Start
Yet to Start
Yet to Start
Yet to Start
Yet to Start
Yet to Start
Yet to Start
Yet to Start
Yet to Start
Yet to Start
Yet to Start
Yet to Start
Yet to Start
Yet to Start
Yet to Start
Yet to Start
Yet to Start
Yet to Start
Yet to Start
Yet to Start
Yet to Start
Yet to Start
Yet to Start
Yet to Start
Yet to Start
Yet to Start
Yet to Start
Yet to Start
Yet to Start
Yet to Start
Yet to Start
Yet to Start
Yet to Start
Yet to Start
Yet to Start
Yet to Start
Yet to Start
Yet to Start
Yet to Start
Yet to Start
Yet to Start
Yet to Start
Yet to Start
Yet to Start
Yet to Start
Yet to Start
Yet to Start
Yet to Start
Yet to Start
Yet to Start
Yet to Start
Yet to Start
Yet to Start
Yet to Start
Yet to Start
Yet to Start
Yet to Start
Yet to Start
Yet to Start
Yet to Start
Yet to Start
Yet to Start
Yet to Start
Yet to Start
Yet to Start
Yet to Start
Yet to Start
Yet to Start
Yet to Start
Yet to Start
Yet to Start
Yet to Start
Yet to Start
Yet to Start
Yet to Start
Yet to Start
Yet to Start
Yet to Start
Yet to Start
Yet to Start
Yet to Start
Yet to Start
Yet to Start
Yet to Start
Yet to Start
Yet to Start
Yet to Start
Yet to Start
Yet to Start
Yet to Start
Yet to Start
Yet to Start
Yet to Start
Yet to Start
Yet to Start
Yet to Start
Yet to Start
Yet to Start
Yet to Start
Yet to Start
Yet to Start
Yet to Start
Yet to Start
Yet to Start
Yet to Start
Yet to Start
Yet to Start
Yet to Start
Yet to Start
Yet to Start
Yet to Start
Yet to Start
Yet to Start
Yet to Start
Yet to Start
Yet to Start
Yet to Start
Yet to Start
Yet to Start
Yet to Start
Yet to Start
Yet to Start
Yet to Start
Yet to Start
Yet to Start
Yet to Start
Yet to Start
Yet to Start
Yet to Start
Yet to Start
Yet to Start
Yet to Start
Yet to Start
Yet to Start
Yet to Start
Yet to Start
Yet to Start
Yet to Start
Yet to Start
Yet to Start
Yet to Start
Yet to Start
Yet to Start
Yet to Start
Yet to Start
Yet to Start
Yet to Start
Yet to Start
Yet to Start
Yet to Start
Yet to Start
Yet to Start
Yet to Start
Yet to Start
Yet to Start
Yet to Start
Yet to Start
Yet to Start
Yet to Start
Yet to Start
Yet to Start
Yet to Start
Yet to Start
Yet to Start
Yet to Start
Yet to Start
Yet to Start
Yet to Start
Yet to Start
Yet to Start
Yet to Start
Yet to Start
Yet to Start
Yet to Start
Yet to Start
Yet to Start
Yet to Start
Yet to Start
Yet to Start
Yet to Start
Yet to Start
Yet to Start
Yet to Start
Yet to Start
Yet to Start
Yet to Start
Yet to Start
Yet to Start
Yet to Start
Yet to Start
Yet to Start
Yet to Start
Yet to Start
Yet to Start
Yet to Start
Yet to Start
Yet to Start
Yet to Start
Yet to Start
Yet to Start
Yet to Start
Yet to Start
Yet to Start
Yet to Start
Yet to Start
Yet to Start
Yet to Start
Yet to Start
Yet to Start
Yet to Start
Yet to Start
Yet to Start
Yet to Start
Yet to Start
Yet to Start
Yet to Start
Yet to Start
Yet to Start
Yet to Start
Yet to Start
Yet to Start
Yet to Start
Yet to Start
Yet to Start
Yet to Start
Yet to Start
Yet to Start
Yet to Start
Yet to Start
Yet to Start
Yet to Start
Yet to Start
Yet to Start
Yet to Start
Yet to Start
Yet to Start
Yet to Start
Yet to Start
Yet to Start
Yet to Start
Yet to Start
Yet to Start
Yet to Start
Yet to Start
Yet to Start
Yet to Start
Yet to Start
Yet to Start
Yet to Start
Yet to Start
Yet to Start
Yet to Start
Yet to Start
Yet to Start
Yet to Start
Yet to Start
Yet to Start
Yet to Start
Yet to Start
Yet to Start
Yet to Start
Yet to Start
Yet to Start
Yet to Start
Yet to Start
Yet to Start
Yet to Start
Yet to Start
Yet to Start
Yet to Start
Yet to Start
Yet to Start
Yet to Start
Yet to Start
Yet to Start
Yet to Start
Yet to Start
Yet to Start
Yet to Start
Yet to Start
Yet to Start
Yet to Start
Yet to Start
Yet to Start
Yet to Start
Yet to Start
Yet to Start
Yet to Start
Yet to Start
Yet to Start
Yet to Start
Yet to Start
Yet to Start
Yet to Start
Yet to Start
Yet to Start
Yet to Start
Yet to Start
Yet to Start
Yet to Start
Yet to Start
Yet to Start
Yet to Start
Yet to Start
Yet to Start
Yet to Start
Yet to Start
Yet to Start
Yet to Start
Yet to Start
Yet to Start
Yet to Start
Yet to Start
Yet to Start
Yet to Start
Yet to Start
Yet to Start
Yet to Start
Yet to Start
Yet to Start
Yet to Start
Yet to Start
Yet to Start
Yet to Start
Yet to Start
Yet to Start
Yet to Start
Yet to Start
Yet to Start
Yet to Start
Yet to Start
Yet to Start
Yet to Start
Yet to Start
Yet to Start
Yet to Start
Yet to Start
Yet to Start
Yet to Start
Yet to Start
Yet to Start
Yet to Start
Yet to Start
Yet to Start
Yet to Start
Yet to Start
Yet to Start
Yet to Start
Yet to Start
Yet to Start
Yet to Start
Yet to Start
Yet to Start
Yet to Start
Yet to Start
Yet to Start
Yet to Start
Yet to Start
Yet to Start
Yet to Start
Yet to Start
Yet to Start
Yet to Start
Yet to Start
Yet to Start
Yet to Start
Yet to Start
Yet to Start
Yet to Start
Yet to Start
Yet to Start
Yet to Start
Yet to Start
Yet to Start
Yet to Start
Yet to Start
Yet to Start
Yet to Start
Yet to Start
Yet to Start
Yet to Start
Yet to Start
Yet to Start
Yet to Start
Yet to Start
Yet to Start
Yet to Start
Yet to Start
Yet to Start
Yet to Start
Yet to Start
Yet to Start
Yet to Start
Yet to Start
Yet to Start
Yet to Start
Yet to Start
Yet to Start
Yet to Start
Yet to Start
Yet to Start
Yet to Start
Yet to Start
Yet to Start
Yet to Start
Yet to Start
Yet to Start
Yet to Start
Yet to Start
Yet to Start
Yet to Start
Yet to Start
Yet to Start
Yet to Start
Yet to Start
Yet to Start
Yet to Start
Yet to Start
Yet to Start
Yet to Start
Yet to Start
Yet to Start
Yet to Start
Yet to Start
Yet to Start
Yet to Start
Yet to Start
Yet to Start
Yet to Start
Yet to Start
Yet to Start
Yet to Start
Yet to Start
Yet to Start
Yet to Start
Yet to Start
Yet to Start
Yet to Start
Yet to Start
Yet to Start
Yet to Start
Yet to Start
Yet to Start
Yet to Start
Yet to Start
Yet to Start
Yet to Start
Yet to Start
Yet to Start
Yet to Start
Yet to Start
Yet to Start
Yet to Start
Yet to Start
Yet to Start
Yet to Start
Yet to Start
Yet to Start
Yet to Start
Yet to Start
Yet to Start
Yet to Start
Yet to Start
Yet to Start
Yet to Start
Yet to Start
Yet to Start
Yet to Start
Yet to Start
Yet to Start
Yet to Start
Yet to Start
Yet to Start
Yet to Start
Yet to Start
Yet to Start
Yet to Start
Yet to Start
Yet to Start
Yet to Start
Yet to Start
Yet to Start
Yet to Start
Yet to Start
Yet to Start
Yet to Start
Yet to Start
Yet to Start
Yet to Start
Yet to Start
Yet to Start
Yet to Start
Yet to Start
Yet to Start
Yet to Start
Yet to Start
Yet to Start
Yet to Start
Yet to Start
Yet to Start
Yet to Start
Yet to Start
Yet to Start
Yet to Start
Yet to Start
Yet to Start
Yet to Start
Yet to Start
Yet to Start
Yet to Start
Yet to Start
Yet to Start
Yet to Start
Yet to Start
Yet to Start
Yet to Start
Yet to Start
Yet to Start
Yet to Start
Yet to Start
Yet to Start
Yet to Start
Yet to Start
Yet to Start
Yet to Start
Yet to Start
Yet to Start
Yet to Start
Yet to Start
Yet to Start
Yet to Start
Yet to Start
Yet to Start
Yet to Start
Yet to Start
Yet to Start
Yet to Start
Yet to Start
Yet to Start
Yet to Start
Yet to Start
Yet to Start
Yet to Start
Yet to Start
Yet to Start
Yet to Start
Yet to Start
Yet to Start
Yet to Start
Yet to Start
Yet to Start
Yet to Start
Yet to Start
Yet to Start
Yet to Start
Yet to Start
Yet to Start
Yet to Start
Yet to Start
Yet to Start
[13 empty] | Yet to Start | Assigned
[13 empty] | In Progress | UnAssigned
ReOpen
On Hold
Resolved
Rejected
Closed